## Proposal Schedule Sample
Para | Task Name | Duration | Start | Finish | Calendar View Start | Calendar View Finish | Time | Predecessors | Reminder Date | Assigned To | % Complete | Status | Comments | Resource Allocation | % Allocation
Proposal Team Assigned
Proposal Coordinator (Lead):
Proposal Support:
Technical SME:
Technical Writer:
Pricing:
Graphics:
Compliance:
DTP:
BEFORE WE BEGIN: CLIENT assumes all responsibilities for final compliance check and acceptance and delivery of the Proposal on time to its end customer.
Sharefile Folder
Solicitation Number:
| SHEET NAME OVERVIEW <INSERT TEAM & PROPOSAL NAME AND DEADLINE>> Team XX - Proposal Name (Due Month, Day, Year) | 52d | 2018-09-11 | 2018-11-01 | [9 empty] | Robert Tucker | 30%
| Proposal Schedule | 55d | 2018-09-11 | 2018-11-05
| Kickoff meeting | 1d | 2018-09-11 | 2018-09-11 | 2018-09-11 | 2018-09-11 |  |  | 2018-09-11
| Send out meeting minutes | 1d | 2018-09-12 | 2018-09-12 |  |  |  |  | 2018-09-12
| Questions for Government | 5d | 2018-10-05 | 2018-10-09 |  |  |  |  | 2018-10-09
| Collect and prepare questions about RFP | 1d | 2018-10-05 | 2018-10-05 |  |  |  |  | 2018-10-05
| Send out for internal review | 1d | 2018-10-05 | 2018-10-05 |  |  |  |  | 2018-10-05
| Prepare Questions to/or submit to Government | 1d | 2018-10-08 | 2018-10-08 |  |  | 5 PM |  | 2018-10-08
| Questions Due to the Government | 1d | 2018-10-09 | 2018-10-09 | 2018-10-09 | 2018-10-09 | 1 PM |  | 2018-10-09
| Pre-Proposal Conference/Site Visit | 1d | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 |  |  | 2018-10-04
| PROPOSAL WRITING | 20d | 2018-09-12 | 2018-10-01 |  |  |  |  | 2018-10-01
| Writing Days | 20d | 2018-09-12 | 2018-10-01 | 2018-09-12 | 2018-10-01 |  |  | 2018-10-01
| Volume I <<INSERT RFP SPECIFICS & SubTasks Below>> Populate from CRM including RFP sections, etc. | 20d | 2018-09-12 | 2018-10-01 |  |  |  |  | 2018-10-01
| Volume II <<INSERT RFP SPECIFICS & SubTasks Below>> Populate from CRM including RFP sections, etc. | 20d | 2018-09-12 | 2018-10-01 |  |  |  |  | 2018-10-01
| Volume III <<INSERT RFP SPECIFICS & SubTasks Below>> Populate from CRM including RFP sections, etc. | 20d | 2018-09-12 | 2018-10-01 |  |  |  |  | 2018-10-01
| Volume IV <<INSERT RFP SPECIFICS & SubTasks Below>> Populate from CRM including RFP sections, etc. | 20d | 2018-09-12 | 2018-10-01 |  |  |  |  | 2018-10-01
| MAJOR MILESTONES | 28d | 2018-10-01 | 2018-10-29 |  |  |  |  | 2018-10-29
| First PENS DOWN - 5 PM | 0 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 5 PM | 27 | 2018-10-01
| Prepare proposal for REVIEW | 1d | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 |  | 30 | 2018-10-02
| Files for REVIEW distributed | 0 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 12 PM | 31 | 2018-10-02
| FIRST REVIEW | 9d | 2018-10-03 | 2018-10-11 |  |  |  |  | 2018-10-11
| REVIEW # 1 | 4d | 2018-10-03 | 2018-10-06 | 2018-10-03 | 2018-10-06 | 5 PM | 32 | 2018-10-06
| Writers Recovery | 5d | 2018-10-07 | 2018-10-11 | 2018-10-07 | 2018-10-11 |  | 34 | 2018-10-11
| SECOND REVIEW (Full Proposal) | 10d | 2018-10-11 | 2018-10-21 |  |  |  |  | 2018-10-21
| PENS DOWN - 5 PM | 0 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 5 PM | 35 | 2018-10-11
| DTP, Compliance Check | 1d | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 12 PM | 37 | 2018-10-12
| REVIEW # 2 | 4d | 2018-10-13 | 2018-10-16 | 2018-10-13 | 2018-10-16 | 1 PM | 38 | 2018-10-16
| Writers Recovery | 5d | 2018-10-17 | 2018-10-21 | 2018-10-17 | 2018-10-21 |  | 39 | 2018-10-21
| THIRD REVIEW (Full Proposal - almost final mode) | 8d | 2018-10-21 | 2018-10-29 |  |  |  |  | 2018-10-29
| PENS DOWN - 5 PM | 0 | 2018-10-21 | 2018-10-21 | 2018-10-21 | 2018-10-21 | 10 AM | 40 | 2018-10-21
| DTP, Compliance Check | 2d | 2018-10-22 | 2018-10-23 | 2018-10-22 | 2018-10-23 | 12 PM | 42 | 2018-10-23
| REVIEW # 3 | 4d | 2018-10-24 | 2018-10-27 | 2018-10-24 | 2018-10-27 | 2 PM | 43 | 2018-10-27
| Writers Recovery | 2d | 2018-10-28 | 2018-10-29 | 2018-10-28 | 2018-10-29 | 5 PM | 44 | 2018-10-29
| FINAL PENS DOWN - 5 PM | 0 | 2018-10-29 | 2018-10-29 | 2018-10-29 | 2018-10-29 | 5 PM | 45 | 2018-10-29
| Prepare files to send to Editor/DTP | 1d | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 12 PM | 46 | 2018-10-30
| Final Review of all Volumes | 1d | 2018-10-31 | 2018-10-31 | 2018-10-31 | 2018-10-31 | 5 PM | 47 | 2018-10-31
| Final Compliance Check and Minor Revisions (if any) | 1d | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 5 PM | 48 | 2018-11-01
| FINAL FILES submitted to client for submission | 0 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 5 PM | 49 | 2018-11-01
| Proposal Due to Government | 0 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 1 PM |  | 2018-11-05